## Product Backlog
ID | Description | Priority | Effort (hours) |  | Status | Remark
|  |  | estimated | required
1 | As a developer, I want a game rules engine that holds the complete game state independently of networking and graphics, so that the rules can be unit-tested in isolation. | 1 | 24 |  | open | Inc1 ¦ D1
2 | As a player, I want to connect my client to the game server, so that I can take part in a match from my own computer. | 1 | 20 |  | open | Inc1 ¦ D2
3 | As a player, I want the server to reject every action that is not valid in the current game state (not my turn, not enough mana, card not in my hand, illegal target), so that nobody can cheat. | 1 | 20 |  | open | Inc1 ¦ D2
4 | As a player, I want the match to run in rounds with a hero phase followed by a Dungeon Master phase, so that everyone knows when it is their turn. | 1 | 12 |  | open | Inc1 ¦ D1
5 | As a player, I want my mana to refill at the start of each round, so that I can play new cards in every round. | 1 | 6 |  | open | Inc1 ¦ D1
6 | As a player, I want my own deck from which I draw cards into my hand, so that I can make tactical choices. | 1 | 12 |  | open | Inc1 ¦ D1
7 | As a hero player, I want to play a card on a target by paying its mana cost, so that I can attack, heal or support. | 1 | 16 |  | open | Inc1 ¦ D1
8 | As a hero player, I want to play as a Warrior or a Cleric, so that I have a distinct role in the party. | 1 | 12 |  | open | Inc1 ¦ D1
9 | As the Dungeon Master, I want to summon a monster on a spawn tile, so that I can block the heroes. | 1 | 12 |  | open | Inc1 ¦ D1
10 | As the Dungeon Master, I want my monsters to act automatically at the end of my phase, so that they threaten the heroes without me controlling every move. | 1 | 14 |  | open | Inc1 ¦ D1
11 | As the Dungeon Master, I want to place a hidden trap that triggers when a hero enters its tile, so that I can surprise the party. | 1 | 10 |  | open | Inc1 ¦ D1
12 | As a player, I want to see the board, my hand, health and mana in a basic 2D view, so that I can follow and play the game. | 1 | 24 |  | open | Inc1 ¦ UI
13 | As a developer, I want every change to be built and tested automatically and reviewed before it is merged, so that broken code never reaches the main branch. | 1 | 4 |  | done | Inc1 ¦ Process
14 | As a hero player, I want to move my hero across a grid-based dungeon with walls and doors, so that I can explore it. | 1 | 16 |  | open | Inc2 ¦ D1
15 | As a hero player, I want to play as a Ranger with ranged attacks, so that the party has more tactical variety. | 1 | 8 |  | open | Inc2 ¦ D1
16 | As a player, I want to create a match in a lobby and let others join it, so that we can start a game together. | 1 | 16 |  | open | Inc2 ¦ D4
17 | As a player, I want to choose my role (hero class or Dungeon Master) in the lobby, so that the team can agree on roles before the match starts. | 1 | 8 |  | open | Inc2 ¦ D4
18 | As a hero player, I want to see only explored rooms and what is in my line of sight, so that the Dungeon Master's preparations stay hidden. | 1 | 16 |  | open | Inc2 ¦ D2
19 | As a hero player, I want the Dungeon Master's hand and hidden traps never to be sent to my client, so that hidden information cannot be read even from a modified client. | 1 | 12 |  | open | Inc2 ¦ D2
20 | As a player, I want my own actions to appear immediately and be corrected if the server rejects them, so that the game feels responsive despite latency. | 1 | 20 |  | open | Inc2 ¦ D3
21 | As a player, I want lost, duplicated or out-of-order messages never to change the game state twice, so that all clients stay consistent. | 1 | 16 |  | open | Inc2 ¦ D2
22 | As a player, I want the server to accept an action only from the player it belongs to, so that nobody can act in my name. | 1 | 10 |  | open | Inc2 ¦ D2
23 | As a player, I want the match to end when the boss is defeated or all heroes are down, and to see a victory or defeat screen, so that I know how the match ended. | 1 | 8 |  | open | Inc2 ¦ D1
24 | As a player, I want legal targets to be highlighted and invalid moves to be explained, so that I understand why an action failed. | 2 | 10 |  | open | Inc2 ¦ UI
25 | As a player, I want a turn timer that ends my turn automatically, so that one player cannot block the match. | 2 | 6 |  | open | Inc2 ¦ D1
26 | As a hero player, I want each class to have a full set of cards, so that every class plays differently. | 2 | 12 |  | open | Inc2 ¦ D1
27 | As a developer, I want card and monster values to be loaded from data files, so that the game can be balanced without recompiling. | 2 | 8 |  | open | Inc2 ¦ D1
28 | As a player, I want to rejoin a running match after losing my connection and receive the current state, so that I can continue playing. | 1 | 20 |  | open | Inc3 ¦ D5
29 | As a player, I want empty seats to be filled by bots that use the same interface as human players, so that we can play with fewer people. | 1 | 24 |  | open | Inc3 ¦ D6
30 | As a developer, I want a fault-injection test harness that simulates 150 to 300 ms latency, 2 to 5 % packet loss and disconnects, so that we can prove clients never desynchronize. | 1 | 24 |  | open | Inc3 ¦ D7
31 | As a player, I want finished matches to be stored with players, roles, result and all actions, so that the history survives a server restart. | 1 | 12 |  | open | Inc3 ¦ D4
32 | As a player, I want to view the history of past matches in the client, so that I can look back at previous games. | 2 | 6 |  | open | Inc3 ¦ D4
33 | As the supervisor, I want the server to run on a machine reachable by all players, so that the demo and the adversarial exercise can take place. | 1 | 8 |  | open | Inc3 ¦ Deployment
34 | As the Dungeon Master, I want my strength to scale with the number of heroes, so that matches with three to six heroes stay balanced. | 2 | 8 |  | open | Inc3 ¦ D1
35 | As the Dungeon Master, I want monster types with different behaviours (melee, ranged), so that I have more tactical options. | 2 | 12 |  | open | Inc3 ¦ D1
36 | As the Dungeon Master, I want environmental events such as a blocked corridor, so that I can change the dungeon during the match. | 2 | 10 |  | open | Inc3 ¦ D1
37 | As a new player, I want a short in-game help screen, so that I can play without an external manual. | 2 | 6 |  | open | Final ¦ UI
38 | As a hero player, I want an alternative objective such as reaching the exit, so that matches can end in different ways. | 3 | 6 |  | open | Inc3 ¦ D1
| Total effort (hours) |  | 488 | 0
Legend
Priority: 1 = high (required for the planned release), 2 = medium (desirable), 3 = low (optional).
Effort: estimated = planning estimate in hours; required = actual hours, filled in after the sprint.
Status: open, planned (in a sprint backlog), done, cancelled.
Remark: planned release (Inc1 until 12.11.2026, Inc2 until 26.11.2026, Inc3 until 10.12.2026, Final 17.12.2026) ¦ deliverable from the topic sheet (D1 to D7) or area.
Non-functional constraints are listed on the sheet "Non-functional Constraints".

## Non-functional Constraints
ID | Category | Constraint | How it is verified | Priority | Planned Release | Source
NF-01 | Architecture | Authoritative server: only the server holds the valid game state; state reported by a client is never trusted. | Code review; adversarial round-robin exercise | 1 | Inc1 | Topic 1 (mandatory)
NF-02 | Security | Every incoming action is validated against the current game state before it is applied. | Unit tests with an illegal input for every action type | 1 | Inc1 | Topic 1 (mandatory)
NF-03 | Security | Information hidden from a player (traps, Dungeon Master's hand, unexplored areas) is never sent to that player's client. | Automated test: the serialized view of every hero contains no hidden data | 1 | Inc2 | Vision
NF-04 | Security | Actions are accepted only from the session of the player they belong to (no identity spoofing). | Test: an action with a forged player ID is rejected | 1 | Inc2 | Vision
NF-05 | Robustness | Lost, duplicated or out-of-order messages never cause an action to be applied twice or the state to become inconsistent. | Fault-injection test with duplicated and reordered messages | 1 | Inc2 | Topic 1 (mandatory)
NF-06 | Responsiveness | Client-side prediction shows the player's own action immediately and is reconciled with the server state when they differ. | Manual and automated test at 300 ms latency | 1 | Inc2 | Topic 1 (mandatory)
NF-07 | Robustness | Clients stay synchronized at 150 to 300 ms latency and 2 to 5 % packet loss. | Fault-injection harness: state hashes of all clients are identical at the end of a match | 1 | Inc3 | Topic 1 (mandatory)
NF-08 | Robustness | A player who reconnects during a match receives a consistent, correct game state within 5 seconds. | Test: disconnect a client mid-match, reconnect and compare state hashes | 1 | Inc3 | Topic 1 (mandatory)
NF-09 | Persistence | The game history survives a restart of the server. | Test: restart server and read history | 1 | Inc3 | Topic 1 (D4)
NF-10 | Performance | One server hosts at least three matches with seven players each on a small virtual machine (1 vCPU, 1 GB RAM). | Load test with bot clients | 2 | Inc3 | Vision
NF-11 | Maintainability | The rules engine has no dependency on networking or graphics code and has its own unit tests. | Build configuration check; unit test report | 1 | Inc1 | Topic 1 (D1)
NF-12 | Platform | Implementation in C++20 with CMake; client runs on Windows and Linux, server on Linux. | CI builds on Windows and Linux | 1 | Inc1 | Vision / DR-001
NF-13 | Process | Source code is managed in Git; every change is built and tested by CI and reviewed in a pull request before merging. | Branch protection on main; pull request history | 1 | Inc1 | Course rules
NF-14 | Usability | A match lasts about 15 to 20 minutes; every turn is limited by a turn timer. | Measured in playtests | 2 | Inc2 | Vision
NF-15 | Usability | A new player can start and play a match without reading an external manual. | Test with a person outside the team | 2 | Final | Vision
NF-16 | Legal | Only open-source libraries whose licences allow use in this project. | Licence list in the architecture notebook | 1 | Inc1 | Vision
NF-17 | Documentation | Architecture notebook with deployment, component, class and entity relationship diagrams, each with an explanation. | Submission review | 1 | 29.10.2026 | Course rules
NF-18 | Documentation | README with build, installation and usage instructions. | Review before final release | 2 | Final | Vision
Priority: 1 = high, 2 = medium, 3 = low. "Topic 1 (mandatory)" marks the architecture constraints from the topic sheet that the supervisor checks explicitly.

## Sprint 1
Sprint 1
Starts | 2018-11-08
Ends | 2018-11-28
Overall Goal | Improve user profile functionality
User Stories that are part of this sprint:
ID | Description | Acceptance Criteria |  |  |  | Status
1 | As a registered user I want to set-up a personal profile page to present myself. | User can define and view profile page with profile picture and self description. |  |  |  | in process
done
to do
accepted
Sprint Backlog (Tasks)
ID | Description | User Story ID | Effort (hours) |  | Status | Person(s)
|  |  | estimated | required
1 | Extend database with fields for profile info | 1 | 3 | 4.5 | done | Philipp Graf
2 | Develop form to fill in profile data in HTML | 1 | 6 |  | in process | Anja Müller
3 | Add form and logic for save / edit to application | 1 | 3 |  | to do

## Sprint x (copy template!)
Sprint 1
Starts
Ends
Overall Goal | <Define: What is overall goal?>
User Stories that are part of this sprint:
ID | Description | Acceptance Criteria |  |  |  | Status
Sprint Backlog (Tasks)
ID | Description | User Story ID | Effort (hours) |  | Status | Persons
|  |  | estimated | required